## Sheet1
Daily Stand-up Meeting Report
Week: Oct 31 - Nov 4
Project Name: Freebies for Newbies
Team Name: 05
| Monday | Wednesday | Friday
Jaichand Mulakalapalli
Adithya Krishna Raavi | We want to do some research on how date picker works | We need to make presentation slides. | We started working on the presentation slides.
| We are searching for better making of UI | We are gathering the requirements for presentation. | We need to adjust the presentation slides.
| NA | NA | NA
Saibabu Devarapalli
Manoj Kumar Gude | Updated event descrpition page | Studied about actionbar and noactionbar | Tried ti implement the action bar code
| Studying about actionbar and noctionbar | Try to implement actionbar and noactionbar | preparing slides for midterm presentation
| NA | NA | NA
Harish Chowdary Bala
Note:
1. What did I accomplish? 2.What will I do today? 3.What obstacles are impeding my progress?