## Sheet1
Daily Stand-up Meeting Report
Week: Feb06 - Feb 10
Project Name: Freebies for Newbies
Team Name: 05
| Monday | Wednesday | Friday
Jaichand Mulakalapalli
Adithya Krishna Raavi
Saibabu Devarapalli
Manoj Kumar Gude | Created activities for Free items | Developed activities for create free item | Integrated and done with testing for free item activity
| Developing free items activities according to the requirements | Integrating UI with backend | Preparing slides for midterm
| NA | NA | NA
Harish Chowdary Bala | We are working on Free items for queries like Request,Update,Delete | Working on database tables functionalities | We are done the create the tables for free items page in databse
| Still working on the queries in Database | Build queries for FreeItems | We are planning to complete the queries for Free Items Page
| NA | NA | NA
Note:
1. What did I accomplish? 2.What will I do today? 3.What obstacles are impeding my progress?