## Sheet1
Daily Stand-up Meeting Report
Week: Feb13 - Feb 17
Project Name: Freebies for Newbies
Team Name: 05
| Monday | Wednesday | Friday
Adithya Krishna Raavi | I have created the UI Request for Event Update Request. | We created FreeItems page | We need to create more pages like Delete Items page.
| We need to create the UI pages for Free Items Update and delete page. | We need to check what are the possibilities that are ther e to add to the page. | These items need to be finalised by the team.
| NA | NA | NA
Saibabu Devarapalli
Manoj Kumar Gude
Harish Chowdary Bala
Note:
1. What did I accomplish? 2.What will I do today? 3.What obstacles are impeding my progress?