## Sheet1
Daily Stand-up Meeting Report
Week: Sept 5 - Sept 9
Project Name: Freebies for Newbies
Team Name: 05
| Monday | Wednesday | Friday
Jaichand Mulakalapalli | NA | Guide team how to use github for Version control | Getting UI/UX design layout from team
| NA | I will be working with team and assist them in pushing the code | I will be writing backend code for the completed layouts
| NA | Merge conflict when two different pushes made | Handling exceptions that occur during user login process
Adithya Krishna Raavi | NA
NA
NA
Saibabu Devarapalli | NA
NA
NA
Manoj Kumar Gude | NA
NA
NA
Harish Chowdary Bala | NA | We getting the information of UI/UX interfaces. | We have done databse ER diagrams and some Login pages.
| NA | I and Chandu are doing the Login authentication process in these week. | We are on the process of login authentication Layouts.
| NA | We or on the process of database layouts and firebase database. | I learning databses like firebase and oracle.
Note:
1. What did I accomplish? 2.What will I do today? 3.What obstacles are impeding my progress?