## Sheet1
Daily Stand-up Meeting Report
Week: Jan 30 - Feb 05
Project Name: Freebies for Newbies
Team Name: 05
| Monday | Wednesday | Friday
Jaichand Mulakalapalli
Adithya Krishna Raavi | Updated UI for event delete request activity. | Complete UI side event page | Knowledge transfer for the integration part
| Adding activites admin functionality activities. | We need to research on admin functionality | Browsing backend checks on back4app Databsefor
| NA | NA | NA
Saibabu Devarapalli
Manoj Kumar Gude
Harish Chowdary Bala
Note:
1. What did I accomplish? 2.What will I do today? 3.What obstacles are impeding my progress?