## Sheet1
Daily Stand-up Meeting Report
Week: Sept 26 - Sept 30
Project Name: Freebies for Newbies
Team Name: 05
| Monday | Wednesday | Friday
Jaichand Mulakalapalli | 1) Learned Android Activity Lifecycle | 1) Completed organizing the folders and files in Github | 1) Completed slides for the Workshop presentation
| 2) Organize the folders and files in Github | 2) Prepare slides for the Workshop presentation | 2) Give workshop presentation on Andriod activity lifecycle and summarize the presentaion.
| 3)NA | 3)NA | 3) Over coming stage fear
Adithya Krishna Raavi | Na | 1.Searched the requirements for workshop. | 1.I completed the ppt my part of presentation.
| Na | 2Did some background work on android studio and layouts. | 2. I completed the analysis requirements of the functionality.
| Na | 3.)Need to make the ppt work greatfully. | 3. I need to work on the functionality no time for coding.Hectic schedule.
Saibabu Devarapalli | 1) Did changes on ER diagram | 1)Prepared Workshop resentation slides on Firebase database and learned queries and architecture. | 1) Finalaized ER diagram and learned about Android studio and how to integrate Firebase Database in Android studio.
| 2) I will prepare workshop presentation document on Firebase databse. | 2) I will give presentaion on Firebase database and will do changes in ER diagram. | 2) I will change the Database based on project requirement.
| 3) NA | 3) NA | 3) We are finalizing the database.
Manoj Kumar Gude | 1)Learned about recycler view and components of the android | 1) Prepared slides for the workshop | 1)I prepared and given presentation today
| 2)Preparing slides for presentation | 2)I will give presentation today | 2)Discussing about pros and cons heroku progress today
| 3)NA | 3) NA | 3) Finalizing the database
Harish Chowdary Bala | Update the database Schema diagram | I learned about Genymotion and virtual box | We are discussing about the next step of the project
| We do presentation about Project workshop | I explain about Genymotion for workshop presentation | 2) The tools we are using like eclipse,virtual box and genymotion are discussing
| NA | 3) | We are taking a step to database
Note:
1. What did I accomplish? 2.What will I do today? 3.What obstacles are impeding my progress?