## Sheet1
Daily Stand-up Meeting Report
Week: Oct 03 - Oct 07
Project Name: Freebies for Newbies
Team Name: 05
| Monday | Wednesday | Friday
Jaichand Mulakalapalli | 1)Learned about Back4App database | 1) Completed login page code using back4app databases | 1) Completed slides for Midterm presentation.
| 2)Work on the backend code for login and home pages | 2) Work on ppt for midterm presentation | 2) work the backend code for Home and recycler Views
| 3) authentication handling with back4app | 3) NA | 3) NA
Adithya Krishna Raavi | 1) Started to work on the functionality. | 1) We completed all the pages and adding actions to the pages. | 1)Added the UI required fields.
| 2) Started to work on the ppt slides. | 2) Checking the APIS for proper functionality. | 2) Changed the string interpolation methods and started working on functionality.
| 3) We need to modify the design. | 3) NA | 3)NA
Saibabu Devarapalli | 1) I have learned topics on how to integrate back4app database in android studio. | 1) Back4app databse integration and created NewBie class in android studio. | 1) I have succesfully executed backend code for registration page.
| 2) I will prepare midterm presentation document and will write backend java code for NewBie class. | 2) Today i will give presentation for Midterm01 and will write backend java code for registartion page. | 2) I will do changes on functionality and will fix errors. will write database queries to fetch data from backend to UI.
| 3) learning queries and login authentication on Back4app. | 3) Encounter errors while connecting user entered data to database. | 3)NA
Manoj Kumar Gude | 1)learned about for back4app | 1)doing some changes in UI and preparing the ppt for midterm | 1)Done with the authentication connection
| 2)doing some changes in UI and preparing the ppt for midterm | 2)Doing authentication connection with the UI page | 2)creating new layouts and updating sample data
| 3)NA | 3)NA | 3)NA
Harish Chowdary Bala | Working on the Next designs | Today we are prepare for the presentation | We are preparing to do the future process in project
| Today we are ready to login page | We have to do functionality process | We are discusssing the future process
| NA | NA | We lag in team discussions
Note:
1. What did I accomplish? 2.What will I do today? 3.What obstacles are impeding my progress?