## Sheet1
Daily Stand-up Meeting Report
Week: Jan 23 - Jan 27
Project Name: Freebies for Newbies
Team Name: 05
| Monday | Wednesday | Friday
Jaichand Mulakalapalli | Successful in assigning the work items to teammates. | Added login functionality for admin | Created admin Home page and added navigation items
| Work on Admin login page. | Working on Admin Home Page. | Need to work on recycler view for Admin approval requests
| na | Waiting on Teams inputs for integrating frontend and backend | Na
Adithya Krishna Raavi | Worked on team goals assign | Discusse don the creation of update page | Need to check that the page is loading or not.
| To work on event detail page | we assigned tasks to create the page | We need to work on the isuue for the admin page.
| NA | Na | Na
Saibabu Devarapalli | I have completed backend code for eventrequest query | added methods in event update request query class | I have created tables in Database
| will do changes in code | will create event update request and event delete request table in Database | will add required fields/attributes in table
| NA | NA | NA
Manoj Kumar Gude | Communicated with team to work on common goals | Done changes in event detail page. | Created event deltion activity.
| To update and delete button for the event detail page | To work on event deletion request activity | To work on menu bar shortcuts.
| NA | NA | NA
Harish Chowdary Bala | Last week we working on queries. | Still working on the Queries and update some fileds in the Database | We are almost done the test queries
| We want to update Event page like Event ID and some fields | We are discussing to complete these process on these weekend | Check the update page and update fields
| Testing the quieries we work on last week | NA | NA
Note:
1. What did I accomplish? 2.What will I do today? 3.What obstacles are impeding my progress?