## Sheet1
Week: Nov 21 - Nov 25
Project Name: Freebies for Newbies
Team Name: 05
| Monday | Wednesday | Friday
Jaichand Mulakalapalli | Divided tasks among the team | Eliminated inconsistencies after layout files modified. | Configured ItemAdapter
| Check on the dependencies after removing and adding the components. | Configure Adapter to handle items recyclerview | Check if all things are used correcly.
| NA | NA | NA
Adithya Krishna Raavi | Need to add the card view layout to the recycler view. | Added the layout constraints to look in a beautiful manner. | Adjusted the spacing issues.
| I will check the layouts of the particular files. | Added the layout and resolved issues. | Added the card view layout to the particular file.
| NA | NA | NA
Saibabu Devarapalli | trying to remove redirect buttons | Removed redirect button from the event detail page | Tried to add toolbar for navigation
| Removed ridirect button in event detail page | Trying to add toolbar for navigation | Added toolbar for the event detail page for navigation
| NA | NA | NA
Manoj Kumar Gude
Harish Chowdary Bala
Note:
1. What did I accomplish? 2.What will I do today? 3.What obstacles are impeding my progress?