## Sheet1
Week: Nov 14 - Nov 18
Project Name: Freebies for Newbies
Team Name: 05
| Monday | Wednesday | Friday
Jaichand Mulakalapalli
Adithya Krishna Raavi | We accomplished date and time picker. | Completed half of the work need to add few more elements | Added the layout for the items page.
| We startted working on items home page. | I will work on adding the rest of the components to finish the layout design. | Need to discuss further tasks that should be taken care for.
| NA | NA | NA
Saibabu Devarapalli | I have modified backedcode on event page and update event using recycler view, intents. | We are successful in fixing the issue with menu item selection. | Added Event Date search Functionality
| I will work on minor enhancement like date search and event search functionality | I need to work on date search functionality. | Need to fix issues
| NA | NA | NA
Manoj Kumar Gude
Harish Chowdary Bala
Note:
1. What did I accomplish? 2.What will I do today? 3.What obstacles are impeding my progress?