## Sheet1
Week: Nov 21 - Nov 25
Project Name: Freebies for Newbies
Team Name: 05
| Monday | Wednesday | Friday
Jaichand Mulakalapalli
Adithya Krishna Raavi | Need to add the card view layout to the recycler view. | Added the layout constraints to look in a beautiful manner. | Adjusted the spacing issues.
| I will check the layouts of the particular files. | Added the layout and resolved issues. | Added the card view layout to the particular file.
| NA | NA | NA
Saibabu Devarapalli | I have designed blueprint for Item Model class | I have written backend code for Item Model class | I have added few changes in Item class.
| I will write backend code for Item Model class | I will add admin functionality. | I will fix issues.
| NA | NA | NA
Manoj Kumar Gude | trying to remove redirect buttons | Removed redirect button from the event detail page | Tried to add toolbar for navigation
| Removed ridirect button in event detail page | Trying to add toolbar for navigation | Added toolbar for the event detail page for navigation
| NA | NA | NA
Harish Chowdary Bala
Note:
1. What did I accomplish? 2.What will I do today? 3.What obstacles are impeding my progress?