## Sheet1
Daily Stand-up Meeting Report
Week: Sept 5 - Sept 9
Project Name: Freebies for Newbies
Team Name: 05
| Monday | Wednesday | Friday
Jaichand Mulakalapalli | 1) I am successful in assembling a team and started learning things that are required for the project | 1) We have came up with a workflow in building the App. Team has been assigned with roles & resposibilities | 1) I am successful in test sample projects in andriod studio and getting familiar with its funtionalities
| 2) We will team disscussion on the design and implementation | 2) Status update. Check with team on their assigned work. | 2) Share steps and information on how to use andriod studio
| 3) Distribution of workload among team .how to use android studio and integrate things? | 3) Handle the exceptions and integration of UI elements with backend code | 3) Come up with layouts that are best suitable for our project. Team will propose different layout designs we will finalize them
Adithya Krishna Raavi | 1) | 1) | 1)
| 2) | 2) | 2)
| 3) | 3) | 3)
Saibabu Devarapalli | 1) Freebies for Newbies is a project that assists new international students and will be helpful to their needs. We decide to cut the project budget and enhance the functioning of a task which results in user friendly Application. | 1) We created a workflow as a team, and we assigned tasks for this week. worked on layout pages, database tools, and software requirements. | 1) worked on the layout of the pages for sign-up and sign-in.
| 2) As a team, we will assign tasks and choose the database and backend technologies that are best for the project. We'll create a blueprint. | 2) We'll take the necessary steps to link user-entered data to the database and get a quick response. Additionally, we will work on page layout and gather team updates. | 2) will focus on how input data from the UI linked to the database and work on backend coding to transfer data from the database to the UI.
| 3) It could be challenging to assign tasks and time complexity. | 3) Conflicts might arise while connecting user-provided data to a database and receiving responses from the database to the front end. | 3) We will learn more about Android Studio and the Firebase database as we gain a better understanding of its basics.
Manoj Kumar Gude | 1) Pitching project idea, discussed pros and cons of project and assigned team members | 1)We as a team discussed about software methodology to follow and discussed about the number of layouts to be placed and software requirements to be installed on every team members device. | 1)Adithya and me shared roles as frontend developers and we are anticipated 5 layout in the application and we discussed with team members about layouts and how layouts has to be designed
| 2) Assigning team member roles to design work flow diagram | 2)Getting knowledge and designing basic layouts of the application | 2)Concentrating on UI and layouts
| 3)Assigning team member roles is bit difficul | 3)Integrating the frontend and database | 3)Finalizing UI design
Harish Chowdary Bala | Present I don't accomplish anything just discuss about project with team members. | .I learn about the firebase database it helps me to do design these project | I learn about MongoDB and Firebase Databse
| Today we discuss about the data of everyone is collected and what type of technologies are used in these design. | Yesterday we discuss about the design of these project and we are working on these assigned work. | 2)I will continue the which work assigned by team discussion.
| We are confusing about team roles and work structure. | I don't know about andriod studio, So I am working on that. | I have no experience and I learning it will take some time.
Note:
1. What did I accomplish? 2.What will I do today? 3.What obstacles are impeding my progress?