## Sheet1
Daily Stand-up Meeting Report
Week: Mar 20 - Mar 24
Project Name: Freebies for Newbies
Team Name: 05
| Monday | Wednesday | Friday
Jaichand Mulakalapalli
Adithya Krishna Raavi
Saibabu Devarapalli
Manoj Kumar Gude
Harish Chowdary Bala | Complete my work in database tables and queries. | Start the test cases of the application and get the some cases where we can update the application | Presented slides for the workshop
| I am going to test the application in these week | Preparing and presenting slides for the workshop | For the next week to do some test cases by using some software.
| NA | NA | NA
Note:
1. What did I accomplish? 2.What will I do today? 3.What obstacles are impeding my progress?