## Sheet1
Daily Stand-up Meeting Report
Week: Mar 27 - Mar 31
Project Name: Freebies for Newbies
Team Name: 05
| Monday | Wednesday | Friday
Jaichand Mulakalapalli |  |  |  | Explore
Adithya Krishna Raavi
Saibabu Devarapalli | I have did few changes on code to fix errors. | I have written backend code for User profile page. | I have fixed erros.
| I will write backend code on user profile page. | I will fix errors. | I will prepare blueprint for documentation.
| NA | NA | NA
Manoj Kumar Gude
Harish Chowdary Bala | Done the my part of database we have no queries in Back4App | Test the cases of user unit on these application | Test multiple test cases and we have decided to change what we to do for that errors.
| I started the testing cases for these application with the help of team | My team are decided to changes some updates on app , so we are discussing the updates | In these we are planning to complete the update and Integration testing
| NA | NA | NA
Note:
1. What did I accomplish? 2.What will I do today? 3.What obstacles are impeding my progress?