## Sheet1
Daily Stand-up Meeting Report
Week: Feb 20 - Feb 24
Project Name: Freebies for Newbies
Team Name: 05
| Monday | Wednesday | Friday
Jaichand Mulakalapalli
Adithya Krishna Raavi
Saibabu Devarapalli
Manoj Kumar Gude
Harish Chowdary Bala | Still working on database for Free Items Page | Done the progress in the databse Free Items Page | Prepare the slides for the next weekpresentation
| We will complete these Page and go with next plans | We will continue the next updates of the Free Items Page | We will work on the presentation Preparation for next week
| NA | NA | NA
Note:
1. What did I accomplish? 2.What will I do today? 3.What obstacles are impeding my progress?