## Sheet1
Daily Stand-up Meeting Report
Week: Oct 31 - Nov 4
Project Name: Freebies for Newbies
Team Name: 05
| Monday | Wednesday | Friday
Jaichand Mulakalapalli
Adithya Krishna Raavi | We want to do some research on how date picker works | We need to make presentation slides. | We started working on the presentation slides.
| We are searching for better making of UI | We are gathering the requirements for presentation. | We need to adjust the presentation slides.
| NA | NA | NA
Saibabu Devarapalli | 1) I have modified Event class and update Event class. | 1) I have modified the model references and adapter references in Home Activity class | 1) I have wrote functionality using Intents.
| 2) I will prepare power point presentation slide on Intents for Workshop. | 2) I will presenation on Intents during class time. | 2) I will prepare presentation slide for Midterm02.
| 3) NA | 3) NA | 3) NA.
Manoj Kumar Gude | Updated event descrpition page | Studied about actionbar and noactionbar | Tried ti implement the action bar code
| Studying about actionbar and noctionbar | Try to implement actionbar and noactionbar | preparing slides for midterm presentation
| NA | NA | NA
Harish Chowdary Bala
Note:
1. What did I accomplish? 2.What will I do today? 3.What obstacles are impeding my progress?