## Sheet1
Daily Stand-up Meeting Report
Week: Sept 19 - Sept 23
Project Name: Freebies for Newbies
Team Name: 05
| Monday | Wednesday | Friday
Jaichand Mulakalapalli | 1). We are successfull in writing a backend code for login and logout | 1). Learned how to use intents in A | 1). Learned about UI design Layouts and few major componets and constraints.
| 2). Learn about intents, activity and bundle | 2). Meet with Professor to finalize the schema | 2). Learning about Recycler Views.
| NA | NA | 3). NA
Adithya Krishna Raavi | 1)NA | 1.) We accomplished all the UI pages. | 1.) we all worked with the ER Diagram and recyclable views.
| 2.)NA | Trying to implement the functionality in UI | 2.) We are working on the functionality.
| 3.)NA | 3.) We need to be more clear on connecting UI and database. | 3.) We need to work more on the front end.
Saibabu Devarapalli | 1) . I have created login fragment in Android studio. | I have made changes in ER diagram and took appointment with Database professor to correct ER diagram. | Me and Harish did changes on ER diagram and added dependies in gradel file in android studio to connect firebase database to Androis studio SDK.
| 2) Today we will design and correct ER diagram. | 2. We'll finalize the ER diagram today using the database professor's inputs. | Based on final ER diagram we will write queries using Firebase database
| 3) Database ER diagram design and gathering queries to create,insert,delete in Firebase database. | 3. I will write backend code to connect frontend to Database. | I am focusing more in advanced topics on Firebasedatabase UI authentication, Firebase UI Firestore, Firebase UI Databse, Firebase UI storage.
Manoj Kumar Gude | 1.Helps with database team to create and to store the registered values. | 1.Studying about how to implement recycler view | Meet database professor and finalized the database schema
| 2. Study about recycler view | 2.Meet database professor to finalize the schema | studying and knowing about toggle bar
| 3. NA | 3. seems to little difficult to know apply new views to enhace UI because there is vast data | NA
Harish Chowdary Bala | We are remove the errors in these code and created a backend and login files. | We are on the process to connecting the firebase to android studio | Me and sai Babu done a schema diagram for Database.
| We have to discuss the schema diagram with professor . | We are draw the schema diagram with the help of Databse professor. | We have to cretae a tables for the Firebase Database.
| The pending work to do a database cloud in these project. | Schema diagram is the pending work of the project | We are discussing the next step in project process.
Note:
1. What did I accomplish? 2.What will I do today? 3.What obstacles are impeding my progress?