## Sheet1
Daily Stand-up Meeting Report
Week: Apr 10- Apr 14
Project Name: Freebies for Newbies
Team Name: 05
| Monday | Wednesday | Friday
Jaichand Mulakalapalli |  |  |  | Explore
Adithya Krishna Raavi
Saibabu Devarapalli | I have did few changes on code to fix errors. | I have written backend code for User profile page. | I have fixed erros.
| I will write backend code on user profile page. | I will fix errors. | I will prepare blueprint for documentation.
| NA | NA | NA
Manoj Kumar Gude
Harish Chowdary Bala | We done the test cases and change the UI part. | We are planning to prepare the slides for presentation like what is the progress of the project | We make the UI changes and done the pages are not overlapping in the application
| We plan to complete the UI part and Integration part of the application. | We successfully complete the presentation | We want to test the application in another way and update the main parts.
| NA | NA | Na
Note:
1. What did I accomplish? 2.What will I do today? 3.What obstacles are impeding my progress?