## Sheet1
Daily Stand-up Meeting Report
Week: Feb06 - Feb 10
Project Name: Freebies for Newbies
Team Name: 05
| Monday | Wednesday | Friday
Jaichand Mulakalapalli | Assigned topics for Workshop presentation | Prepared Slides for the workshop1 presentation | Work on the Admin Event update request model
| Work on the admin event update request page | Give presentaion to the audience | Complete the rest of the module for Event Update Requests Page
| NA | NA | NA
Adithya Krishna Raavi | We discussed on how to make presentation | I made the presentation slides | We planned on UI
| We gathered the requirements that need | We added the new things that we learnt in presentation slides | We are making the changes according to it.
| NA | NA | NA
Saibabu Devarapalli | 1. I have created tables in Database and we are able to store data. | 1. I have prepared presentation slides. | 1. I have did few changes in backend code.
| 2. I will prepare slides for workshop01 presentation | 2. I will write back end code for event delete request class | 2. I will add few admin functionalities.
| 3. NA | 3. NA | 3. NA
Manoj Kumar Gude | created and done changes in the event delete detail page | Created slides for the workshop | Planned new layouts for the free events
| Creating slides for workshop | Planning new layouts for the free event page | Creating activities like create activities for free activity.
| NA | NA | NA
Harish Chowdary Bala | I have created tables and queries in Databse | We present the presentation in the workshop | We are planning to completing these work schedules
| We are prepare the slides for workshop presntation | We are planning to completing these work schedule | We are stuck in these functionalities and planning to complete
| NA | NA | NA
Note:
1. What did I accomplish? 2.What will I do today? 3.What obstacles are impeding my progress?