## Sheet1
Daily Stand-up Meeting Report
Week: Sept 12 - Sept 16
Project Name: Freebies for Newbies
Team Name: 05
| Monday | Wednesday | Friday
Jaichand Mulakalapalli | 1) I got the layout designs and specifications from Manoj and Adithya | 1) We are checking all the possibilities for API's | 1) I am able build java code and processed Registration and login authentication successful
| 2)I will be working on the backend code for Registration page/layout | 2) I will be checking how API's are working in Android to firebase database. | 2) Learn about API and other things
| 3)NA | NA | 3) How to store user data and other data in firebase database
Adithya Krishna Raavi | 1) We designed layouts without functinality. | 1) We are writing functionality and developing the code. | 1) I have written the logic for login and register pages and removed some fragments and written in the activities for connecting withdatabase.
| 2)We need confirmation of the backend to integrate with UI | 2) We saw some references in online and i think we are good to create a datbase tables | 2) We nned to connect full fledged backend withbUI.
| 3) NA | 3)NA | 3) NA
Saibabu Devarapalli | 1) By last sprint we did layout designs and generetaed output in Android studio. | 1)Waiting for prior approval to go ahead with creation of databases.and connecting to backend. | 1) I have written java code and processed Registration and login authentication successful.
| 2) I will do backedn code for Login page | 2) Adjusted the Er diagrams and did some changes. | 2) I will write Queries to connect frontend to Database.
| 3) NA | 3) So far we are good. | 3) I will learn queries to create, insert and delete operations in table.
Manoj Kumar Gude | 1. We completed the initial layouts of login and register page. | 1)Finding out bugs in code | 1)Designed home page
| 2. We need to make it functional. | 2)Fixing buds in xml code and desigining page xml part | 2)Fixing bugs in previous pages
| 3. Finding bugs in code. | 3)Finding out missing values | 3)NA
Harish Chowdary Bala | We are done the layouts of authentication pages. | There are some issues in layout designs. | Connected Firebae databse to the Android Studio using the (firebase.google.com).
| I will work on databse architecture to connect user data from android studio to Fire base Database | We have to work on that issues and move to another step. | We are running the buildscipt on Android studio and gradle the project to the build success.
| Last week I work on datbase ER diagrams they are some mistakes in mys side | I am watching firebase databse process videos it will help to connect android studio | To create tables and how to insert data to the tables in these firebase.
Note:
1. What did I accomplish? 2.What will I do today? 3.What obstacles are impeding my progress?