## Sheet1
Daily Stand-up Meeting Report
Week: Jan 30 - Feb 06
Project Name: Freebies for Newbies
Team Name: 05
| Monday | Wednesday | Friday
Jaichand Mulakalapalli
Saibabu Devarapalli
Manoj Kumar Gude | Done changes in layout adding relative layout for some attributes in event delete request and event detail activity which are overlapping. | Integrated UI with backend | Created demo layouts for admin
| Integrating UI with backend code | Creating demo layouts for Admin | Creating UI for admin activities
| NA | NA | NA
Harish Chowdary Bala | We working on the event update queries | We completed the event page and queris in my side | Still working on the backend for database
| Decided to finish this things in these weekend | Today onwards my role is testing the functionalities | On next week we start the testing part
| NA | NA | NA
Note:
1. What did I accomplish? 2.What will I do today? 3.What obstacles are impeding my progress?