## Sheet1
Daily Stand-up Meeting Report
Week: Apr 17- Apr 21
Project Name: Freebies for Newbies
Team Name: 05
| Monday | Wednesday | Friday
Jaichand Mulakalapalli | SendGrid Email alerts have been delivered successfully | Verified Email alerts for respective activities | Working on fixing the bugs related to session time out | Explore
| Check on Email alerts for respective activities | Work on fixing the bugs related to session time out | Work on different solution for session time out
| NA | NA | Need to figure out the bug in code
Adithya Krishna Raavi | I written the code in create events page. | I written the code and fixed soe basic functions. | I written the documentation in the word format
| Fixed some bugs on UI layouts. | I written the code in the login page. | I am working on documentation.
| NA | NA | NA
Saibabu Devarapalli | I have did few changes on code to fix errors. | I have written backend code for User profile page. | I have fixed erros.
| I will write backend code on user profile page. | I will fix errors. | I will prepare blueprint for documentation.
| NA | NA | NA
Manoj Kumar Gude | Done changes in the UI to overlapping attributes | Tested the overlapping attributes | Implemented references in documentation.
| Testing the attributes which are overlapping | Implementing references in documentation | Work on overlapping issues in UI.
| NA | NA | NA
Harish Chowdary Bala | We done the test cases and change the UI part. | We are planning to done the errors in the application | We make the UI changes and done the pages are not overlapping in the application
| We plan to complete the Documentation of the application. | We successfully complete the overlapping part | The team to plan complete the documenation in next week
| NA | NA | Na
Note:
1. What did I accomplish? 2.What will I do today? 3.What obstacles are impeding my progress?